## Working route
Blackboard Group No 08 Class ZEE | Project kickoff |  |  |  |  | Version 1 |  |  |  |  | Version 2 (optional) |  |  |  |  | Version 3 (option) |  |  |  |  | Final Submit (and version 3 Pro option)
SMART goals ==> | Specific activities | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING (not) DONE DONE LATE HUNG UP | Specific activities | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING (not) DONE DONE LATE HUNG UP | Specific activities | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING (not) DONE DONE LATE HUNG UP | Specific activities | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING (not) DONE DONE LATE HUNG UP | Specific activities | How is deliverable Measured? Is delivery criteria Agreed? | Realistic planned hours actual hours | planned date & Time of delivery actual date & time | Status TO DO DOING (not) DONE DONE LATE HUNG UP
|  | PM class date | =====> | 2021-11-25 |  |  |  | PM class date plus | 8 | days |  |  | PM class date plus | 13 | days |  |  | PM class date plus | 14 | days | Last possible submit date: | 2021-12-09 | PM class plus | 14 | days
Each group member | Project Mgmt Activity | share with team |  | 2021-11-26 | DONE
Group Meeting Agenda ==> | create MS Team Private Channel; for Version 1, create plan with SMART goals and assign tasks | detailed tasks assigned to group members with est. hrs., agreed upon delivery date to Teams, updated Status | 1.5 | 2021-11-26 | DONE | review progress, refine plan, update DONE items with actual hours, refine estimates and delivery date/time | In MS Team Channel, select any file you would like reviewed and send a message @instructor to comment on that file. |  | Tuesday Nov.30 | DONE | Group decision whether to do this version. If so, members plan to complete V2 of their module. | detailed tasks assigned to group members with est. hrs., agreed upon delivery date/time to Teams, updated Status |  | Sunday Dec.5 | TO DO | Group decision whether to do this version. If so, members plan to complete V3 of their module. | detailed tasks assigned to group members with est. hrs., agreed upon delivery date/time to Teams, updated Status |  | Monday Dec.6 | TO DO | Submit final version of artefacts from Teams to Blackboard. Backup Teams files. | updated DONE items below with actual hours. |  | Monday Dec.6 | TO DO
Usama Sidat Fundamentals | Keeping a record of everyone's files | Work done; Yes, Agreed. | One hour Same | 2021-11-26 | DONE | Completing all files related to fundamentals module | Quite Good; Yes; Agreed | Two Hours | Wednesday Dec.1 | DONE | Completing all files related to fundamentals module along with git files. | Excellent; Everything Agreed. | 2.5 Hours | Monday Dec.6 | DONE | Completing all files related to fundamentals module along with git files of version 3. | Normal Yes; All Good | 2 Hours | Tuesday Dec.7 | DONE |  |  |  | Wednesday Dec.8
Anmol Kataria Manipulating | Sending all the files to team leader | Work done; Yes, Agreed. | One hour Same | 2021-11-26 | DONE | Completing all files related to manipulating module | Quite Good; Yes; Agreed | Two Hours | Wednesday Dec.1 | DONE | Completing all files related to manipulating module along with git files. | Excellent; Everything Agreed. | 2.5 Hours | Monday Dec.6 | DONE | Completing all files related to manipulating module along with git files of version 3. | Normal Yes; All Good | 2 Hours | Tuesday Dec.7 | DONE |  |  |  | Wednesday Dec.8
Khizar Mehmood Tokenizing | Creating Channel on MS Teams | Work done; Yes, Agreed. | One hour Same | 2021-11-26 | DONE | Completing all files related to tokenizing module | Quite Good; Yes; Agreed | Two Hours | Wednesday Dec.1 | DONE | Completing all files related to tokenizing module along with git files. | Excellent; Everything Agreed. | 2.5 Hours | Monday Dec.6 | DONE | Completing all files related to tokenizing module along with git files of version 3. | Normal Yes; All Good | 2 Hours | Tuesday Dec.7 | DONE |  |  |  | Wednesday Dec.8
Sameer Ali Converting, Compiling, Submission. | Planning meeting dates and details of files in compiling | Work done; Yes, Agreed. | One hour Same | 2021-11-26 | DONE | Completing all files related to converting module; Compiling and checking execution of all coding files; Other extra files like testing and plan assessment. | Quite Good; Yes; Agreed | Two Hours | Thursday Dec.2 | DONE | Completing all files related to converting module along with git files.; Compiling and checking execution of all coding files; Other extra files like testing and plan assessment. | Excellent; Everything Agreed. | 2.5 Hours | Tuesday Dec.7 | DONE | Completing all files related to converting module along with git files.; Compiling and checking execution of all coding files; Other extra files like testing and plan assessment of the final version. | Normal Yes; All Good | 2 Hours | Thursday Dec.9 | DONE |  |  |  | Wednesday Dec.8
Note on A2: Use SMART goals to achieve the Triple Constraint of Cost/Resource vs Time/Schedule vs Scope/Quality.
Note on B2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on C2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on D2: How many hours will the task take?
Note on E2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on F2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: an objective or task according to a Time based target – hours of effort completed by a due date & time DONE: an objective or task Measured as completed HUNG UP: no longer doing something because it became unRealistic. Tell the team right away.
Note on G2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on H2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on I2: How many hours will the task take?
Note on J2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on K2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: an objective or task according to a Time based target – hours of effort completed by a due date & time DONE: an objective or task Measured as completed HUNG UP: no longer doing something because it became unRealistic. Tell the team right away.
Note on L2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on M2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on N2: How many hours will the task take?
Note on O2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on P2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: an objective or task according to a Time based target – hours of effort completed by a due date & time DONE: an objective or task Measured as completed HUNG UP: no longer doing something because it became unRealistic. Tell the team right away.
Note on Q2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on R2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on S2: How many hours will the task take?
Note on T2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on U2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: an objective or task according to a Time based target – hours of effort completed by a due date & time DONE: an objective or task Measured as completed HUNG UP: no longer doing something because it became unRealistic. Tell the team right away.
Note on V2: Who does What to produce the project artefacts? Each cell has one or more bullet points on that person's action items. {Alt+Enter} for new line within cell.
Note on W2: This is the result of the Specific action. What is the definition of done? What will you deliver that someone can see, read, use? How will you know it has the minimum acceptable quality? Everyone understands what everyone else is doing to avoid both duplication of effort and omission of details. Interactions and dependencies between individuals is recognized and negotiated.
Note on X2: How many hours will the task take?
Note on Y2: When will the product of the specific action be delivered? Can it be done in the time available? Does everyone have the resources they need soon enough to complete their work by the milestone date? Think Critical Path: One person's end date may be another's start date.
Note on Z2: Each person is their own project manager… TO DO: Specific objectives and tasks which were Agreed upon DOING: an objective or task according to a Time based target – hours of effort completed by a due date & time DONE: an objective or task Measured as completed HUNG UP: no longer doing something because it became unRealistic. Tell the team right away.